## Estimation
Module | Tasks | Estimated Time hr. | Client Feedback | Developer Feedback
Notes:
Datebase | Firebase Firestore
Code Pattern | Bloc
Code storage | Github
Platforms | Android, IOS, Web, Desktop
Custom Search Platfrom | Algolia
Authentication | Phone/Email OTP varification
Session Time | 5 to 8 Min.
Set up | Theme Setup (Light and Dart and system modes)
Spash screen / App Icon (With Slogan)
Route navigation (Go router)
Firebase flavors (Staging and Production)
Bloc setup (To manage state, and saparate logic from UI)
Language localisation (Multiple as you want - it will be applied on labels)
Remote config (For update app dialog, and other)
People looking for booking services
Sign In/ Sign Up | Welcome screen
Sign in with Phone number
Sign in with Email
Social media account (Google, Apple, Facebook)
Forgot Password
User Profile | User information and update functionality
Manage Notification (Here we will use firebase function)
Handle push notification using Firebase
Email and SMS notification (Letter we do after discuss, for it we will need third party)
Change password
Update email
Delete account
Home screen (Restraurants list) | fetch stream list from firebase with pagination
Search:
Keyword
Dropdown with category
Location based (area wise)
Search inside area map
Restaurant details | Restaurant information
Restaurant Location
Add to fevorite
Restaurant Timing
Features ¦ Menu
Restaurant photos
Also we add dynamic attributes for hide unhide some functions
Review:
Customer info (Name, Profile)
Review with date time
Review Images
Filter Review
Review Chart
Chat | Chat with restaurant (Encrypted)
Send Image
Send text
Chat using SMS
Add call option to book with Phone
Send Notification both side
Report Messages both side
Confirmation of booking | Booking: (Check realtime availibility)
Fill Form
Find a table date & time (Lunch,Dinner) & number of guests,
verify and update booking details,
apply offer code, and book
Payment method (Stripe)
Cancel booking:
why you’re canceling order choose in dropdown
Refund payment
Notification to user both case
Booking history | Booking list with status
Saprate booking status wise
Book again with availibility
Booking Details
Payment | Payment using
Stripe
Paypal
ApplePay
Google Pay
Settings | Localization Languages
Change Currency
Offline Capability | Letter we do after discuss (Firebase is allowing this feature)
Analytics | Number of confirmed booking
Number of cancellations
Satisfaction of customers
Average time of booking
Number Search
Testing and Quality Assurance | Unit test for perticuler repository
Integration testing for perticuler module
Business Model and Monetisation | Here we add app subscription and add status in database with date time
We can add service charge on withdraw for stores.
Maintenance and Updates | Bug fixes
OS updates
interoperability
Security update
Systematic reviews/Audit (Quarterly )
Owner of restaurant
Submit request to add restaurant in app | Firebase auth with email/password, or phone/otp.
User will be created with pending approval status.
Add/Update Restaurants | Name, Location, Contact details etc.
Photos, videos, and cutome attrubutes
Request | It will display users who want to book appoinment for table or slot
Can accept or decline request
Chat | Chat with customer when request come
Text, Image, Video, Audio.
Analytics | How many request between date range
How many approved/cancelled between date range
Can be more based on requirement.
Payment | Add bank detail or stripe connect
Current balance
Transaction history (Withdraw or in review)
Add/Update/Remove staff users | Can create users with role
Role will define access
Invitation will be sent to email
List of users (Staff) | owner willl able to view each users profile
Super admin
Users | Can see users with role
Role wise filter
Search with algolia (name, restaurant or other)
Requests | List of users for adding them as store owner
Payment | User will submit reuqest for withdraw
Admin will approve or decline it.
Admin will procced the payment and payment staus will be update here.
Graphs and statistics | Display how many reuest in date range
Display approved user in date range
How many bookings in date range
how many withdraws between date range
earnings